## Slide 1: New and improved lounge booking system for fly dream air
Presented by Macrosoft

## Slide 2: Justification of Project selection
Macrosoft chose Project 3 as it achieved FlyDreamAir’s objectives and criteria’s the highest weighted score.
Project 3 scored the highest in providing support for key business objectives, having a positive NPV, stakeholder satisfaction, and has the lowest risk in achieving cost, time, and scope goals
Project 1 scored the highest in cost and benefits, it scored lower in other criteria, resulting in a lower weighted score of 66
Project 2 scored well in stakeholder satisfaction but scored lower in other critical criteria, resulting in a lower weighted score of 59.5.
Criteria | Weight | Flight Management System | Loyalty Program Management System | Airport Lounge Management System
Support key Business Objectives | 20% | 90 | 60 | 90
Provides Positive NPV | 10% | 40 | 50 | 70
Stakeholder Satisfaction | 5% | 80 | 70 | 60
Has Low Risk in achieving Cost, Time and Scope Goals | 15% | 30 | 50 | 60
Cost and Benefits | 15% | 70 | 40 | 50
User Acceptance | 10% | 20 | 30 | 80
Levels of Risk and Contraints | 25% | 80 | 70 | 80
Weighted Project Scores | 100% | 66 | 59.5 | 78.5

## Slide 3: Business case
Situation Analysis of Existing Business
Analysis of costs vs benefits
FEASIBILITY Study
Swot analysis

## Slide 4: Situation Analysis of Existing Business
Poor Customer Service
Long waiting times
Inadequate occupancy Management
Customer Dissatisfaction
Double booking
Poor user interface

## Slide 5: Analysis of costs vs benefits

## Slide 6: Feasibility study
Technical Feasibility
Financial Feasibility
Legal Feasibility
Operational Feasibility
Compatibility
Security
Scalability
Reliability
Integration
Mobile Optimisation
Budget
Funding
Revenue Projections
Financial Risk
Cash Flow Analysis
Data Protection and security
Compliance with Aviation Regulation
Intellectual Property Rights
Employment Laws
Data Protection and security
Compliance with Aviation Regulation
Intellectual Property Rights
Employment Laws

## Slide 7: Swot analysis
Strengths
Weaknesses
Opportunities
Threats

## Slide 8: Project Charter
Project Title: Airport Lounge Management System
Date Of Authorisation: 26th of May (Friday) 2023
Project Start Date: 29th May (Mon),2023
Project Finish Date: xxxx

## Slide 9: Project Charter
Key Schedule Milestones
Budget Information
Project Manager
Project Objectives
Main Project Success Criteria:
Approach:
Roles And Responsibilities

## Slide 10: Project Scope statement
Project Title: Airport Lounge Management System
Date: 29th May (Mon),2023
Prepared By: Bradley Harris

## Slide 11: Project scope statement
Project Summary and Justification
Product Characteristics and Requirements
Summary of Project Deliverables
1. Project management-related deliverables:
2. Product-related deliverables:
Project Success Criteria:

## Slide 12: WBS

## Slide 13: Risk Management
Identification
Assessment
Mitigation

## Slide 14: Risk Identification
Macrosoft utilised various techniques to determine the potential risks to the development of FlyDream Air’s new lounge booking system.
Techniques included:
Brainstorming
Interviews
Assessing a previous, similar project’s risk register

## Slide 15: Risk Assessment
Each risk identified from the previous step was then analysed to define the risk’s impact severity and probability of it occurring. Subsequently, each risk was then plotted on a probability-impact matrix with the following descriptors:
Probability | Chance of happening
High | Greater than 60%
Significant | 31-60%
Moderate | 15-30%
Low | Less than 15%
Impact Severity | Percentage of budget required to overcome risk’s impact
High | Greater than 25%
Significant | 16-25%
Moderate | 5-15%
Low | Up to 5%

## Slide 16: Probability-Impact Matrix
Items A1, B1 and D2 were identified to be significant risks.
A1 – Delivered product’s function doesn’t meet project requirements.
B1 – Everchanging project requirements
D2 – Project not completed within planned time.
Impact | High | A3 | A1 | B1 | 
 | Significant | A2 | C2 |  | 
 | Moderate | C3 | C1 C4 | D1 | D2
 | Low |  | D3 |  | 
 |  | Low | Moderate | Significant | High
 | Probability |  |  |  | 

## Slide 17: Risk Mitigation
All risks identified and assessed in the previous steps were then given mitigation strategies and contingency plans.
Close monitoring of the high-risk items (A1, B1, D2) to ensure timely action.
Category | ID | Risk Description | Mitigation Strategies
Technical | A1 | Delivered product’s function doesn’t achieve project requirements. | Weekly meetings, assess development progress. Clear goals. Project state re-assessed at milestones.
Technical | A2 | New system won’t integrate with existing system. | Ensure development compliments existing system. Prepare thorough implementation plan. Prepare maintenance plan.
Technical | A3 | The project is too complex. | Limit project scope if necessary. Hire additional project members with appropriate skillset.
Requirements | B1 | Everchanging project requirements. | Efficiently communicate with stakeholder(s). Weekly meetings to keep project team updated.
People | C1 | Team-member absences delaying project. | Distribute workload evenly amongst remaining team-members. Project lead informed of absences promptly.
People | C2 | Low productivity. | Implement methods to promote involvement and team cohesion. Communicate team expectations.
People | C3 | Insufficient skills or training. | Provide training in any new technologies required for development. Ensure project team has diverse set of skills.
People | C4 | Unforeseen, non-work-related circumstances resulting in team absences. | Distribute workload evenly amongst remaining team-members. Utilise project slack if necessary. Propose overtime work.
People | C5 | Insufficient communication leading to confusion. | Maintain weekly meetings. Strengthen project member’s communication skills via training.
Resources | D1 | Exceeding budget. | Maintain scope. Follow resource management plan. Minimise errors and wasted resources.
Resources | D2 | Project not completed within planned time. | Conduct regular team meetings. Adaptive scheduling. Continually measure and assess ongoing progress.
Resources | D3 | Lack of resources due to supply issues. | Ensure sufficient communication with suppliers to notify if any disruption. Have alternate suppliers.